## Sheet1
Name of the Production, CTP #, Date & Milestone (eg. Unsung CTP 111 14/5/10, Milestone 4)
Expenses by Category | Actual Costs Paid to Date | OutstandingAccurals to Date | Total Costs to Date | Estimated Costs to Complete | Estimated Final Costs | Approved Budget | Variance
| A | B | A + B = C | D | C + D = E | F | F - E = G
ABOVE THE LINE:
Producer | 10000 | 2000 | 12000 | 8000 | 20000 | 20000 | 0
Director | 25000 | 0 | 25000 | 5000 | 30000 | 30000 | 0
Consultant (Te Reo Māori) | 4000 | 1000 | 5000 | 1000 | 6000 | 6000 | 0
Writers/Research | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presenter | 10000 | 2000 | 12000 | 0 | 12000 | 12000 | 0
Above The Line SUB TOTAL | 49000 | 5000 | 54000 | 14000 | 68000 | 68000 | 0
BELOW THE LINE:
Production
Production Manager | 15000 | 1500 | 16500 | 3000 | 19500 | 18000 | -1500
Production Assistant | 12000 | 0 | 12000 | 0 | 12000 | 12000 | 0
Camera Crew & Equipment | 28000 | 4000 | 32000 | 0 | 32000 | 30000 | -2000
Sound Recordist & Equipment | 8000 | 0 | 8000 | 0 | 8000 | 8000 | 0
Lighting Crew & Equipment | 1800 | 0 | 1800 | 0 | 1800 | 2000 | 200
Wardrobe/Makeup | 6000 | 0 | 6000 | 0 | 6000 | 5000 | -1000
Studio/Locations | 40000 | 5000 | 45000 | 0 | 45000 | 50000 | 5000
Accommodation/Per Diems | 9600 | 1400 | 11000 | 0 | 11000 | 12000 | 1000
Travel | 3000 | 500 | 3500 | 1000 | 4500 | 3600 | -900
Wardrobe/Makeup | 6500 | 0 | 6500 | 0 | 6500 | 6500 | 0
Production SUB TOTAL | 129900 | 12400 | 142300 | 4000 | 146300 | 147100 | 800
Post Production
Music Copyright | 3500 | 2500 | 6000 | 0 | 6000 | 6500 | 500
Archival/Copyright | 6000 | 0 | 6000 | 0 | 6000 | 5000 | -1000
Tapestock | 4000 | 500 | 4500 | 0 | 4500 | 4500 | 0
Picture Post Production | 50000 | 20000 | 70000 | 12300 | 82300 | 80000 | -2300
Audio Post Production | 15000 | 5000 | 20000 | 3000 | 23000 | 25000 | 2000
Titles/Graphics | 5000 | 3000 | 8000 | 2000 | 10000 | 10000 | 0
Post Production SUB TOTAL | 83500 | 31000 | 114500 | 17300 | 131800 | 131000 | -800
Marketing & Admin
Office Rental | 9000 | 1000 | 10000 | 2000 | 12000 | 12000 | 0
Office Expenses | 4000 | 750 | 4750 | 250 | 5000 | 5000 | 0
Insurance/Finance/Legal | 2100 | 900 | 3000 | 0 | 3000 | 3000 | 0
Marketing & Admin SUB TOTAL | 15100 | 2650 | 17750 | 2250 | 20000 | 20000 | 0
Below The Line SUB TOTAL | 228500 | 46050 | 274550 | 23550 | 298100 | 298100 | 0
Above The Line SUB TOTAL | 49000 | 5000 | 54000 | 14000 | 68000 | 68000 | 0
TOTAL Above & Below the Line | 277500 | 51050 | 328550 | 37550 | 366100 | 366100 | 0
Contingency (up to 10% BTL) | 12000 | 0 | 12000 | 0 | 12000 | 12000 | 0
Production Company Overhead (PCO) (up to 10% BTL) | 0 | 0 | 0 | 21900 | 21900 | 21900 | 0
TOTAL COSTS | 289500 | 51050 | 340550 | 59450 | 400000 | 400000 | 0